## Gantt
|  | SEMANA | [16 empty] | TOTAL HORAS
TAREA |  | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | Planifs | Reales | Faltan/ Sobran
T1 | Interfaz Grafica frames y layouts | 5 | 5 | 5 | 5 | 5 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 41 | 40 | 1
T2 | Jtable y mapa rutas |  |  |  | 5 | 5 | 10 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 36 | 36 | 0
T3 | renderizados | [5 empty] | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 24 | 25 | -1
T4 | Eventos | [6 empty] | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 24 | 20 | 4
T5 | Hilos y animaciones |  |  |  | 2 | 2 | 2 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 25 | 34 | -9
T6 | Registros en bases de datos | 2024-11-18: 10; 2024-11-25: 10; 2024-12-02: 10; 2024-12-09: 10; 2024-12-16: 10; 2025-01-13: 3; 2025-01-20: 3 | 56 | 60 | -4
T7 | Recursividad | 2024-12-02: 10; 2024-12-09: 10; 2024-12-16: 10; 2024-12-23: 10; 2024-12-30: 10; 2025-01-13: 3; 2025-01-20: 3 | 56 | 20 | 36
T8 | optimizacion del proyecto | 2024-12-16: 5; 2024-12-23: 5; 2024-12-30: 5; 2025-01-06: 5; 2025-01-13: 3; 2025-01-20: 3 | 26 | 10 | 16
T9 | Decoracion de la aplicacion | 2024-11-11: 5; 2024-12-09: 5; 2024-12-23: 2; 2024-12-30: 2; 2025-01-06: 2; 2025-01-13: 3; 2025-01-20: 3 | 22 | 5 | 17
T10 | solucion de fallos | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 36 | 10 | 26
| TOTAL HORAS | 7 | 7 | 7 | 14 | 14 | 21 | 29 | 17 | 17 | 27 | 32 | 32 | 24 | 24 | 14 | 30 | 30 | 346 | 260 | 86

## HorasTotales
Total | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | TOTAL
T1 | 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
T2 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
T3 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
T4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
T5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
T6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
T7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
T8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
T9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
T10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Cesar Manuel Llata Remacha
TAREA | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | TOTAL
T1 | 2024-09-30: 2; 2024-10-07: 5; 2024-10-14: 5; 2024-10-21: 5; 2024-10-28: 5; 2024-11-04: 6; 2024-11-11: 0; 2024-12-09: 2 | 30
T2 | 2024-10-21: 5; 2024-10-28: 5; 2024-11-04: 4; 2024-11-11: 5; 2024-12-09: 2 | 21
T3 | 2024-11-04: 8; 2024-11-11: 9; 2024-12-02: 5 | 22
T4 | 2024-11-11: 8 | 8
T5 | 2024-11-11: 3 | 3
T6 | 2024-11-25: 5; 2024-12-02: 5; 2024-12-09: 5; 2024-12-16: 5; 2024-12-23: 5; 2024-12-30: 5 | 30
T7 | [17 empty] | 0
T8 | 2024-12-23: 2; 2024-12-30: 2; 2025-01-06: 1 | 5
T9 | 2024-12-09: 6 | 6
T10 | 2024-11-18: 11; 2024-12-23: 2; 2024-12-30: 2; 2025-01-06: 1 | 16
TOTAL | 2 | 5 | 5 | 10 | 10 | 18 | 25 | 11 | 5 | 10 | 15 | 5 | 9 | 9 | 2 | 0 | 0 | 141

## Julen Anda Gómez
TAREA | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | TOTAL
T1 | 2024-09-30: 5; 2024-10-07: 5; 2024-10-14: 5; 2024-10-21: 2; 2024-11-04: 1; 2024-11-11: 1; 2024-11-25: 1; 2024-12-02: 1 | 21
T2 | 2024-11-04: 6; 2024-11-11: 3 | 9
T3 | 2024-11-04: 0; 2024-11-11: 0 | 0
T4 | 2024-11-11: 2 | 2
T5 |  |  |  | 2 | 2 | 2 | 2 | 5 | 20 | 10 | 10 |  |  | 2 | 2 | 5 |  | 62
T6 | [17 empty] | 0
T7 | [17 empty] | 0
T8 | 2024-12-23: 1; 2024-12-30: 2; 2025-01-06: 2 | 5
T9 | 2024-12-09: 4; 2024-12-23: 1; 2024-12-30: 2; 2025-01-06: 2 | 9
T10 | 2024-11-18: 5; 2024-12-09: 6; 2024-12-30: 2; 2025-01-06: 2; 2025-01-13: 1 | 16
TOTAL | 5 | 5 | 5 | 4 | 2 | 9 | 8 | 10 | 21 | 11 | 20 | 0 | 2 | 8 | 8 | 6 | 0 | 124